## EXAMPLE - System FMEA
Example System FMEA Template
Project Name | [5 empty] | FMEA ID |  | Revision | Date
Project Phoenix | [5 empty] | 000123 |  | 1.0 | 09/30/20XX
System Name |  |  |  | Subsystems |  |  |  |  | Date Completed
XYZ Powertrain System |  |  |  | Transmission, Cooling System, Electrical System |  |  |  |  | 00/00/20XX
Team | [6 empty] | Party Responsible |  | Approved By
Jose Price (System Engineer), Marta Hicks (Quality Engineer), Jonathon Wong (Reliability Engineer) | [6 empty] | Jose Price |  | Diana Kennedy
System Failure Mode and Effects Analysis (FMEA) | [10 empty] | RPN Columns contain a formula to auto-calculate; do not alter or delete. |  |  |  | System FMEA Results
ID | System / Subsystem | Function | Potential Failure Mode | Effects of Failure | Severity | Causes | Occurrence | Current Controls |  | Detection | RPN | Recommended Actions | Owner | Date Due | Action Results | Date Completed | Severity | Occurrence | Detection | RPN
# | Name, ID number, etc. | Primary function | How could the system / subsystem potentially fail? | Consequential impact on other systems, depts., etc. |  | All contributing factors |  | Prevention | Detection |  | Risk Priority Number | Steps required to reduce severity, occurrence, and detection | Organization, team, or individual responsible | Target date of completion | actions taken | actual date of completion |  |  |  | Risk Priority Number
1 | Power Distribution | Distribute power to subsystems | Power overload | System shutdown, safety hazard | 9 | Incorrect load calculation | 6 | Load balancing | Circuit breakers | 3 | 162 | Review load calculations, upgrade breakers | Jose Price | 10/10/20XX | Load calculations updated | 10/11/20XX | 7 | 4 | 3 | 84
2 | Cooling Management | Maintain engine temperature | Overheating | Engine damage, performance loss | 8 | Radiator malfunction | 5 | Coolant monitoring | Temperature sensors | 4 | 160 | Add backup cooling system | Marta Hicks | 10/15/20XX | Backup system installed | 10/16/20XX | 6 | 3 | 2 | 36
3 | Transmission Control | Shift gears effectively | Gear slippage | Reduced acceleration, increased wear | 7 | Gear misalignment | 6 | Gear alignment checks | Wear sensors | 5 | 210 | Improve gear alignment process | Jonathon Wong | 10/20/20XX | Alignment process revised | 10/20/20XX | 5 | 4 | 3 | 60
4 | Fuel Injection | Inject fuel at correct rate | Incorrect fuel rate | Engine performance issues, emissions increase | 8 | Sensor failure | 4 | Regular sensor calibration |  | 3 | 96 | Implement real-time monitoring | Jose Price | 10/25/20XX | Monitoring system added | 10/22/20XX | 6 | 3 | 2 | 36
5 | Exhaust Management | Expel exhaust gases | Exhaust blockage | Emissions increase, power loss | 7 | Catalyst degradation | 5 | Emissions testing | Visual inspection | 4 | 140 | Replace catalyst material | Marta Hicks | 10/30/20XX | New catalyst installed | 10/28/20XX | 5 | 3 | 2 | 30
6 | Electrical System | Power electronic components | Short circuit | Component failure, system restart | 9 | Insulation failure | 4 | Insulation checks | Circuit protection | 3 | 108 | Use higher-grade insulation | Jonathon Wong | 11/05/20XX | Insulation upgraded | 11/02/20XX | 7 | 3 | 2 | 42
7 | Braking System | Provide braking force | Brake fade | Reduced braking efficiency, safety risk | 9 | Overheating brake pads | 6 | Temperature monitoring |  | 4 | 216 | Upgrade brake pads, improve cooling | Jose Price | 11/10/20XX | Brake pads replaced | 11/08/20XX | 7 | 4 | 3 | 84
8 |  |  |  |  | 8 |  | 9 |  |  | 10 | 720 | [8 empty] | 0
9 |  |  |  |  | 9 |  | 10 |  |  | 10 | 900 | [8 empty] | 0
10 |  |  |  |  | 10 |  | 10 |  |  | 10 | 1000 | [8 empty] | 0
11 | [10 empty] | 0 | [8 empty] | 0
12 | [10 empty] | 0 | [8 empty] | 0
13 | [10 empty] | 0 | [8 empty] | 0
14 | [10 empty] | 0 | [8 empty] | 0
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - System FMEA
System FMEA Template
Project Name | [5 empty] | FMEA ID |  | Revision | Date
System Name |  |  |  | Subsystems |  |  |  |  | Date Completed
Team | [6 empty] | Party Responsible |  | Approved By
System Failure Mode and Effects Analysis (FMEA) | [10 empty] | RPN Columns contain a formula to auto-calculate; do not alter or delete. |  |  |  | System FMEA Results
ID | System / Subsystem | Function | Potential Failure Mode | Effects of Failure | Severity | Causes | Occurrence | Current Controls |  | Detection | RPN | Recommended Actions | Owner | Date Due | Action Results | Date Completed | Severity | Occurrence | Detection | RPN
# | Name, ID number, etc. | Primary function | How could the system / subsystem potentially fail? | Consequential impact on other systems, departments, etc. |  | All contributing factors |  | Prevention | Detection |  | Risk Priority Number | Steps required to reduce severity, occurrence, and detection | Organization, team, or individual responsible | Target date of completion | actions taken | actual date of completion |  |  |  | Risk Priority Number
1 | [10 empty] | 0 | [8 empty] | 0
2 | [10 empty] | 0 | [8 empty] | 0
3 | [10 empty] | 0 | [8 empty] | 0
4 | [10 empty] | 0 | [8 empty] | 0
5 | [10 empty] | 0 | [8 empty] | 0
6 | [10 empty] | 0 | [8 empty] | 0
7 | [10 empty] | 0 | [8 empty] | 0
8 | [10 empty] | 0 | [8 empty] | 0
9 | [10 empty] | 0 | [8 empty] | 0
10 | [10 empty] | 0 | [8 empty] | 0
11 | [10 empty] | 0 | [8 empty] | 0
12 | [10 empty] | 0 | [8 empty] | 0
13 | [10 empty] | 0 | [8 empty] | 0
14 | [10 empty] | 0 | [8 empty] | 0
15 | [10 empty] | 0 | [8 empty] | 0
16 | [10 empty] | 0 | [8 empty] | 0
17 | [10 empty] | 0 | [8 empty] | 0
18 | [10 empty] | 0 | [8 empty] | 0
19 | [10 empty] | 0 | [8 empty] | 0
20 | [10 empty] | 0 | [8 empty] | 0
21 | [10 empty] | 0 | [8 empty] | 0
22 | [10 empty] | 0 | [8 empty] | 0
23 | [10 empty] | 0 | [8 empty] | 0
24 | [10 empty] | 0 | [8 empty] | 0
25 | [10 empty] | 0 | [8 empty] | 0
26 | [10 empty] | 0 | [8 empty] | 0
27 | [10 empty] | 0 | [8 empty] | 0

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS | RATING
Yes | Low | Not Started | 1
No | Medium | In Progress | 2
| High | Complete | 3
|  | Needs Review | 4
|  | Approved | 5
|  | Overdue | 6
|  | On Hold | 7
8
9
10

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.